## Sheet 1
Department of Public Works and Highways
Contract ID:
Contract Name:
Location of the Contract:
Construction Schedule
Name of Contractor:
Note: Entries are provided as illustrative example only.
ITEM NO. | DESCRIPTION | UNIT | QUANTITY | UNIT COST | TOTAL COST |  | % WEIGHT | M O N T H L Y A C C O M P L I S H M E N T
[6 empty] | CD |  | 1st MONTH | 2nd MONTH | 3rd MONTH | 4th MONTH | 5th MONTH | 6th MONTH | 7th MONTH | 8th MONTH | 9th MONTH | 10th MONTH | 11th MONTH | 12th MONTH | 13th MONTH | 14th MONTH
[8 empty] | 30 C.D. | 60 C.D. | 90 C.D. | 120 C.D. | 150 C.D. | 180 C.D. | 210 C.D. | 240 C.D. | 270 C.D. | 300 C.D. | 330 C.D. | 360 C.D. | 390 C.D. | 420 C.D.
PART A | FACILITIES FOR THE ENGINEER
A.1.1(a) | Provide Temporary Field Office Laboratory and Living Quarters for the Engineer and ADB-PMO Staff (on Rental Basis) | mo. | 3 | 26320 | 78960 | 90 | 0.03251% | 0.01084% | 0.01084% | 0.01084%
[22 empty] | TRUE | 0.03251% | 0.03251%
A.1.1(b) | Operate and Maintain Temporary Field Office, Laboratory and Living Quarters for the Engineer and ADB-PMO Staff | mo. | 3 | 67352.88 | 202058.64 | 90 | 0.0832% | 0.02773% | 0.02773% | 0.02773%
[22 empty] | TRUE | 0.0832% | 0.0832%
A.1.1(c) | Provide Combined Field Office and Laboratory Building for the Engineer and ADB-PMO Staff | l.s. | 1 | 3626951.7 | 3626951.7 | 90 | 1.494% | 0.4978% | 0.4978% | 0.4978%
[22 empty] | TRUE | 1.494% | 1.494%
A.1.1(d) | Provide Living Quarters for the Engineer and ADB-PMO Staff | l.s. | 1 | 3613894.6 | 3613894.6 | 420 | 1.488% | 0.496% | 0.496% | 0.496%
[22 empty] | TRUE | 1.488% | 1.488%
A.1.1(e) | Operate/Maintain Combined Field Office, Laboratory and Living Quarters for the Engineer and ADB-PMO Staff (Schedule A) | mo. | 11 | 172491.71 | 1897408.81 | 330 | 0.7813% |  |  |  | 0.07103% | 0.07103% | 0.07103% | 0.07103% | 0.07103% | 0.07103% | 0.07103% | 0.07103% | 0.07103% | 0.07103% | 0.07103%
[22 empty] | TRUE | 0.7813% | 0.7813%
A.1.1(f) | Furnish Equipment, Furniture/Fixtures and Appliances for the Combined Field Office, Laboratory and Living Quarters for the Engineer and ADB-PMO Staff (Schedules B and C) | l.s. | 1 | 1775040.55 | 1775040.55 | 90 | 0.7309% | 0.2436% | 0.2436% | 0.2436%
[22 empty] | TRUE | 0.7309% | 0.7309%
A.1.1(g) | Provide and Maintain Laboratory Testing Equipment and Apparatus (Schedule D) | l.s. | 1 | 1579701.7 | 1579701.7 | 90 | 0.6505% | 0.2168% | 0.2168% | 0.2168%
[22 empty] | TRUE | 0.6505% | 0.6505%
A.1.1(h) | Provide and Maintain Communication Facility for the Engineer | mo. | 14 | 17860 | 250040 | 420 | 0.103% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354% | 0.007354%
[22 empty] | TRUE | 0.103% | 0.103%
A.1.1(i) | Provide Supplies and Consumable Stores for Field Office, Laboratory and Living Quarters for the Engineer and ADB-PMO Staff (Schedules E & F) | mo. | 14 | 108753.49 | 1522548.86 | 420 | 0.627% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478% | 0.04478%
[22 empty] | TRUE | 0.627% | 0.627%
A.1.2(a) | Provide, Operate and Maintain Pick-up Type or its equivalent brand new diesel engine with complete accessories for the Engineer (4 units) | veh-mo. | 56 | 148426 | 8311856 | 420 | 3.423% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445% | 0.2445%
[22 empty] | TRUE | 3.423% | 3.423%
A.1.3(a) | Provide and Maintain Survey Instruments/Equipment for the Assistance to the Engineer (Schedule G) | mo. | 14 | 36735.2 | 514292.8 | 420 | 0.2118% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513% | 0.01513%
[22 empty] | TRUE | 0.2118% | 0.2118%
A.1.3(b) | Provision of Survey Personnel (Schedule H) | mo. | 14 | 100674 | 1409436 | 420 | 0.5804% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146% | 0.04146%
[22 empty] | TRUE | 0.5804% | 0.5804%
A.1.4 | Progress Photographs | set | 14 | 6448.4 | 90277.6 | 420 | 0.03717% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655% | 0.002655%
[22 empty] | TRUE | 0.03717% | 0.03717%
PART B | OTHER GENERAL REQUIREMENTS
SPL-1 | Construction Safety and Health | l.s. | 1 | 1792624.71 | 1792624.71 | 420 | 0.7382% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273% | 0.05273%
[22 empty] | TRUE | 0.7382% | 0.7382%
SPL-2 | Environmental and Social Safeguards | l.s. | 1 | 880140.8 | 880140.8 | 420 | 0.3624% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589% | 0.02589%
[22 empty] | TRUE | 0.3624% | 0.3624%
SPL-3 | Project Billboard | each | 5 | 10528 | 52640 | 37 | 0.02168% | 0.02168%
[22 empty] | TRUE | 0.02168% | 0.02168%
PART C | EARTHWORKS
101(3) | Removal of Existing Asphalt Concrete Pavement | sq.m. | 1885 | 200.34 | 377640.9 | 45 | 0.1555% |  |  | 0.1555%
[22 empty] | TRUE | 0.1555% | 0.1555%
105(2) | Subgrade Preparation (Existing Pavement) | sq.m. | 66005 | 35.03 | 2312155.15 | 255 | 0.9521% |  |  | 0.1143% | 0.1143% | 0.1143% | 0.1143% | 0.1143% | 0.1143% | 0.1143% | 0.1143% | 0.03808%
[22 empty] | TRUE | 0.9521% | 0.9521%
SPL108 | Crack and Seat (Existing Portland Cement Concrete Pavement) | sq.m. | 5000 | 703.83 | 3519150 | 150 | 1.449% |  |  | 0.2898% | 0.2898% | 0.2898% | 0.2898% | 0.2898%
[22 empty] | TRUE | 1.449% | 1.449%
PART E | SURFACE COURSES
300 | Aggregate Surface Course Compacted in Place | cu.m. compacted in place | 9901 | 931.01 | 9217930.01 | 180 | 3.796% | [9 empty] | 0.3374% | 1.265% | 1.265% | 0.9279%
[22 empty] | TRUE | 3.796% | 3.796%
301(1) | Bituminous Prime Coat, MC-70 Cut-Back Asphalt | tonne | 2 | 72942.46 | 145884.92 | 195 | 0.06007% |  |  | 0.03004% | 0.03004%
[22 empty] | TRUE | 0.06007% | 0.06007%
302(2) | Bituminous Tack Coat, Emulsified Asphalt, SS-1 | tonne | 97 | 75221.52 | 7296487.44 | 285 | 3.005% |  |  | 0.09548% | 0.2865% | 0.3819% | 0.3819% | 0.3819% | 0.3819% | 0.3819% | 0.331% | 0.191% | 0.191%
[22 empty] | TRUE | 3.005% | 3.005%
310(1) | Bituminous Concrete Surface (Wearing) Course, Hot Laid (50mm thick) | sq.m. | 42588 | 944.6 | 40228624.8 | 187 | 16.57% |  |  |  | 1.329% | 2.658% | 2.658% | 2.658% | 2.658% | 2.658% | 1.949%
[22 empty] | TRUE | 16.57% | 16.57%
310(2) | Bituminous Concrete Surface (Wearing) Course, Hot Laid (80mm thick) | sq.m. | 89483 | 1314.24 | 117602137.92 | 277 | 48.43% |  |  | 2.549% | 4.248% | 4.248% | 5.777% | 5.777% | 5.777% | 5.777% | 5.777% | 4.248% | 4.248%
[22 empty] | TRUE | 48.43% | 48.43%
310(3) | Bituminous Concrete Surface (Wearing) Course, Hot Laid (100mm thick) | sq.m. | 1177 | 1584.27 | 1864685.79 | 90 | 0.7678% |  |  | 0.3839% | 0.3839%
[22 empty] | TRUE | 0.7678% | 0.7678%
SPL 312 | Sealing of Cracks and Joints in Existing Portland Cement Concrete Pavement | l.m. | 500 | 135.78 | 67890 | 81 | 0.02796% |  |  | 0.01677% | 0.01118%
[22 empty] | TRUE | 0.02796% | 0.02796%
SPL 313 | Patching of Potholes in Existing Asphalt Concrete Pavement | sq.m. | 1000 | 4309.91 | 4309910 | 187 | 1.775% |  |  |  | 0.0986% | 0.2958% | 0.2958% | 0.2958% | 0.2958% | 0.2958% | 0.1972%
[22 empty] | TRUE | 1.775% | 1.775%
PART F | BRIDGE CONSTRUCTION (MACASOY)
101(2) | Removal of Concrete Bridge Structures | each | 1 | 1485575.35 | 1485575.35 | 45 | 0.6117% |  |  | 0.6117%
[22 empty] | TRUE | 0.6117% | 0.6117% | TRUE
101(3)a | Removal of Existing Concrete Pavement (230mm) | sq.m. | 274.73 | 394.95 | 108504.61 | 53 | 0.04468% | [10 empty] | 0.04468%
[22 empty] | TRUE | 0.04468% | 0.04468% | TRUE
102(2)a | Roadway Excavation (Surplus Common) | cu.m. | 865.66 | 150.19 | 130013.48 | 45 | 0.05354% | [10 empty] | 0.05354%
[22 empty] | TRUE | 0.05354% | 0.05354% | TRUE
103(1)a | Structure Excavation (Common Soil) | cu.m. | 95.78 | 326.57 | 31278.87 | 15 | 0.01288% |  |  | 0.01288%
[22 empty] | TRUE | 0.01288% | 0.01288% | TRUE
103(2)a | Bridge Excavation (Soft Rock) | cu.m. | 236.54 | 1252.57 | 296282.91 | 23 | 0.122% |  |  | 0.122%
[22 empty] | TRUE | 0.122% | 0.122% | TRUE
105(1) | Subgrade Preparation (Common Material) | sq.m. | 274.73 | 35.72 | 9813.36 | 7 | 0.004041% | [10 empty] | 0.004041%
[22 empty] | TRUE | 0.004041% | 0.004041% | TRUE
200 | Aggregate Subbase Course | cu.m. | 82.42 | 1521.63 | 125412.74 | 21 | 0.05164% | [10 empty] | 0.05164%
[22 empty] | TRUE | 0.05164% | 0.05164% | TRUE
400(4)a | Precast Concrete Pile, Furnished (400mmx400mm-type B) | l.m. | 120 | 6098.03 | 731763.6 | 75 | 0.3013% |  |  |  | 0.06027% | 0.1808% | 0.06027%
[22 empty] | TRUE | 0.3013% | 0.3013% | TRUE
400(14)a | Precast RC Piles, (Driven) | l.m. | 112 | 3171.96 | 355259.52 | 21 | 0.1463% | [5 empty] | 0.1463%
[22 empty] | TRUE | 0.1463% | 0.1463% | TRUE
400(16)a | Test Piles, Furnished and Driven (400mm x 400mm) | l.m. | 30 | 6333.57 | 190007.1 | 35 | 0.07824% |  |  | 0.03353% | 0.04471%
[22 empty] | TRUE | 0.07824% | 0.07824% | TRUE
401(2) | Concrete Railing Type (Double) | l.m. | 40 | 4559.15 | 182366 | 30 | 0.0751% | [9 empty] | 0.06258% | 0.01252%
[22 empty] | TRUE | 0.0751% | 0.0751% | TRUE
404(b) | Reinforcing Steel Bar, Grade 60 Bridge Structures & Other Major Structures) | kgs. | 25577.53 | 56.43 | 1443340.02 | 180 | 0.5943% | [5 empty] | 0.1829% | 0.1829% | 0.2286%
[22 empty] | TRUE | 0.5943% | 0.5943% | TRUE
404(c) | Reinforcing Steel Bar, Grade 40 (Minor Structures) | kgs. | 2065.8 | 65.2 | 134690.16 | 21 | 0.05546% | [9 empty] | 0.05546%
[22 empty] | TRUE | 0.05546% | 0.05546% | TRUE
405(b) | Structural Concrete, Class A, Major Structures-Bridge Superstructures (fc'=28MPa) | cu.m. | 72.16 | 13235.71 | 955088.83 | 30 | 0.3933% | [8 empty] | 0.3277% | 0.06555%
[22 empty] | TRUE | 0.3933% | 0.3933% | TRUE
405(c) | Structural Concrete, Class A, Major Structures-Bridge Superstructures (fc'=20.7MPa) | cu.m. | 91.5 | 12527.44 | 1146260.76 | 37 | 0.472% | [7 empty] | 0.4563% | 0.01573%
[22 empty] | TRUE | 0.472% | 0.472% | TRUE
405(d) | Structural Concrete, Class A, Major Structures-Bridge Footing (fc'=20.7MPa) | cu.m. | 62.3 | 8472.33 | 527826.16 | 22 | 0.2174% | [6 empty] | 0.2101% | 0.007245%
[22 empty] | TRUE | 0.2174% | 0.2174% | TRUE
405(2)b | Structural Concrete, Class B, (Lean Concrete) | cu.m. | 2.86 | 12431.42 | 35553.86 | 8 | 0.01464% | [6 empty] | 0.01464%
[22 empty] | TRUE | 0.01464% | 0.01464% | TRUE
406(1)c | Prestressed Structural Concrete Members (Girder Type IV-25 meters) | l.m. | 4 | 1054892.27 | 4219569.08 | 150 | 1.738% |  |  |  | 0.1316% | 0.3949% | 0.3949% | 0.3949% | 0.3949% | 0.02633%
[22 empty] | TRUE | 1.738% | 1.738% | TRUE
412 | Elastomeric Bearing Pad | each | 8 | 17180.8 | 137446.4 | 7 | 0.0566% | [8 empty] | 0.0566%
[22 empty] | TRUE | 0.0566% | 0.0566% | TRUE
505(6) | Grouted Riprap, (Class B) | cu.m. | 584.67 | 6029.94 | 3525525.02 | 45 | 1.452% | [8 empty] | 0.7722% | 0.6795%
[22 empty] | TRUE | 1.452% | 1.452% | TRUE
506 | Stone Masonry | cu.m. | 95.78 | 5954.48 | 570320.09 | 7 | 0.2348% | [9 empty] | 0.2348%
[22 empty] | TRUE | 0.2348% | 0.2348% | TRUE
PART H | MISCELLANEOUS STRUCTURES
605(1)a | Warning Signs, Reflective | each | 40 | 23801.64 | 952065.6 | 45 | 0.392% | [10 empty] | 0.392%
[22 empty] | TRUE | 0.392% | 0.392% | TRUE
605(2) | Regulatory Signs, Reflective | each | 36 | 7605.04 | 273781.44 | 45 | 0.1127% | [10 empty] | 0.1127%
[22 empty] | TRUE | 0.1127% | 0.1127% | TRUE
605(3) | Informatory Signs, Reflective | each | 27 | 9934.85 | 268240.95 | 30 | 0.1105% | [10 empty] | 0.1105%
[22 empty] | TRUE | 0.1105% | 0.1105% | TRUE
612(1) | Reflectorized Thermoplastic Pavement Markings, (White) | sq.m. | 5913 | 1034.57 | 6117412.41 | 30 | 2.519% | [12 empty] | 2.519%
[22 empty] | TRUE | 2.519% | 2.519% | TRUE
612(2) | Reflectorized Thermoplastic Pavement Markings, (Yellow) | sq.m. | 934 | 1069.03 | 998474.02 | 30 | 0.4112% | [12 empty] | 0.4112%
[22 empty] | TRUE | 0.4112% | 0.4112% | TRUE
620 | Chevron Signs | each | 230 | 5999.11 | 1379795.3 | 30 | 0.5682% | [10 empty] | 0.0947% | 0.4735%
[22 empty] | TRUE | 0.5682% | 0.5682% | TRUE
PART J | MOBILIZATION AND DEMOBILIZATION
SPL 800 | Mobilization and Demobilization (1% Civil Work Cost) | l.s. | 1 | 1974000 | 1974000 | 60 | 0.8129% | 0.271% | 0.271% | [11 empty] | 0.271%
[22 empty] | TRUE | 0.8129% | 0.8129% | TRUE
PART K | DAYWORKS
SPL 900 | Dayworks | P.S | 1 | 0 | 0 |  | 0% | [15 empty] | 100% | 100%
PART L | PROVISIONAL SUM | [21 empty] | 0%
SPL 1000 | Provisional Sum | P.S. | 1 | 0 | 0 | 60/25 | 0%
| TOTAL |  |  |  | 242846037.34 |  | 100%
SCHEDULED ACCOMPLISHMENT |  |  | MONTHLY |  |  |  | (%) | 2.22% | 2.198% | 6.342% | 7.533% | 9.069% | 10.81% | 10.82% | 10.82% | 10.93% | 10.31% | 7.124% | 6.683% | 4.364% | 0.7765%
|  |  | CUMULATIVE |  |  |  | (%) | 2.22% | 4.418% | 10.76% | 18.29% | 27.36% | 38.17% | 48.99% | 59.81% | 70.74% | 81.05% | 88.18% | 94.86% | 99.22% | 100%
SCHEDULED CASH FLOW |  |  | MONTHLY |  |  |  | Php | 5391262.6421 | 5338622.6421 | 15401606.3632 | 18293852.3099 | 22022523.3814 | 26242933.8068 | 26287107.3814 | 26274163.9955 | 26545168.5536 | 25036055.2616 | 17300637.3669 | 16229788.1809 | 10596736.8324 | 1885578.6221
|  |  | CUMULATIVE |  |  |  | Php | 5391262.6421 | 10729885.2843 | 26131491.6475 | 44425343.9574 | 66447867.3388 | 92690801.1455 | 118977908.527 | 145252072.5224 | 171797241.0761 | 196833296.3377 | 214133933.7046 | 230363721.8855 | 240960458.7179 | 242846037.34
DPWH-INFR-46-2016
0.41519
49.84%
25.82%
75.66%
16341897.92